## Bug Report Log
Bug ID | Module | Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Environment | Linked TC ID | Reported By | Date Found
BUG-01 | Employee API | Duplicate email crashes the server instead of a clean validation error | 1) Create an employee with email X 2) Create another employee with the same email X | API returns 400 with message like 'Email already registered' | API returns 500 Internal Server Error (unhandled DB unique-constraint exception) | Medium | Medium | Open | Python 3.11, FastAPI 0.115.0, SQLite, local (uvicorn dev server) | TC-02 | Tanisha | 2026-09-23
BUG-02 | Leave Request API | Leave request accepted with end date earlier than start date | POST /leave-requests with start_date=2026-10-10, end_date=2026-10-05 | API rejects with 400 'end_date must be on/after start_date' | Request is accepted and stored as a valid PENDING request | High | High | Open | Python 3.11, FastAPI 0.115.0, SQLite, local (uvicorn dev server) | TC-04 | Tanisha | 2026-09-23
BUG-03 | Approval Workflow | No status guard on approve - requests can be approved twice, or approved after rejection | 1) Approve a PENDING request 2) Call approve again on the same id -- OR -- 1) Reject a PENDING request 2) Call approve on the same id | API returns 400 'request already processed' in both cases; balance unaffected | Request is (re-)approved successfully and leave balance is deducted again | Critical | Critical | Open | Python 3.11, FastAPI 0.115.0, SQLite, local (uvicorn dev server) | TC-08, TC-10 | Tanisha | 2026-09-23
BUG-04 | Approval Workflow | Leave balance not validated before approval - can go negative | 1) Employee has 10 days remaining 2) Submit and approve a 30-day leave request | API rejects with 400 'insufficient leave balance' | Request is approved; employee's leave_balance becomes -20 | Critical | Critical | Open | Python 3.11, FastAPI 0.115.0, SQLite, local (uvicorn dev server) | TC-09 | Tanisha | 2026-09-23
BUG-05 | Leave Request API | No duplicate/overlap check on leave request submission | 1) Submit a leave request for 2026-10-01 to 2026-10-05 2) Submit another request for the same employee, same dates | API rejects with 400/409, or flags the overlap for review | Duplicate request is accepted with no warning or conflict check | Medium | Low | Open | Python 3.11, FastAPI 0.115.0, SQLite, local (uvicorn dev server) | TC-11 | Tanisha | 2026-09-23